## LC (2)
[7 empty] | Feb | [16 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | Jun
[7 empty] | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Store | Section | Space (sq ft) | Task | Start Date | End Date | Days | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
IFC | Retail | 3004 | Concept & Design Rendering | 2026-02-12 | 2026-03-31 | 47 | March T 31: 28+2
IFC | Retail | 3004 | Detailed Drawings Package | 2026-03-31 | 2026-04-20 | 20 | April M 20: 11; April T 21: 39 days
IFC | Retail | 3004 | Landlord Sign Off and Approvals | 2026-04-20 | 2026-05-15 | 25
IFC | Retail | 3004 | Hoarding | 2026-05-15 | 2026-05-31 | 16
IFC | Retail | 3004 | Launch | 2026-05-31 | 2026-06-10 | 10
IFC | Retail | 3004 | Merchandising | 2026-06-10 | 2026-07-15 | 35
IFC | F&B | 1200 | Concept & Design Rendering | 2026-02-12 | 2026-03-31 | 47 | March T 31: 28+2
IFC | F&B | 1200 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0
IFC | F&B | 1200 | Licensing Submission | 2026-03-01 | 2026-04-20 | 50
IFC | F&B | 1200 | Detailed Drawings Package | 2026-03-31 | 2026-04-20 | 0 | April M 20: 11; April T 21: 39 days
IFC | F&B | 1200 | Landlord Sign Off and Approvals | 2026-04-20 | 2026-05-15 | 25
IFC | F&B | 1200 | Hoarding | 2026-05-15 | 2026-05-31 | 16
IFC | F&B | 1200 | Provisional License in Place | 2026-05-31 | 2026-07-20 | 50
IFC | F&B | 1200 | Launch | 2026-07-20 | 2026-09-15 | 57
Pacific Place | Retail | 863 | Concept & Design Rendering | 2026-02-12 | 2026-04-15 | 62 | April W 15: 36
Pacific Place | Retail | 863 | Detailed Drawings Package | 2026-04-15 | 2026-05-01 | 16 | May T 5: 13; May W 6: 49 days
Pacific Place | Retail | 863 | Landlord Sign Off and Approvals | 2026-05-01 | 2026-06-01 | 31
Pacific Place | Retail | 863 | Hoarding | 2026-06-01 | 2026-06-20 | 19
Pacific Place | Retail | 863 | Launch | 2026-06-20 | 2026-07-05 | 15
Pacific Place | Retail | 863 | Merchandising | 2026-07-05 | 2026-09-01 | 58
Pacific Place | F&B | 500 | Concept & Design Rendering | 2026-02-12 | 2026-04-15 | 62 | April W 15: 36
Pacific Place | F&B | 500 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0
Pacific Place | F&B | 500 | Licensing Submission | 2026-03-01 | 2026-05-01 | 61
Pacific Place | F&B | 500 | Detailed Drawings Package | 2026-05-01 | 2026-05-01 | 0 | May T 5: 13; May W 6: 49 days
Pacific Place | F&B | 500 | Landlord Sign Off and Approvals | 2026-05-01 | 2026-06-01 | 31
Pacific Place | F&B | 500 | Hoarding | 2026-06-01 | 2026-06-20 | 19
Pacific Place | F&B | 500 | Provisional License in Place | 2026-06-20 | 2026-07-05 | 15
Pacific Place | F&B | 500 | Launch | 2026-07-05 | 2026-08-20 | 46
Pacific Place | F&B | 500 | Final Launch | 2026-08-20 | 2026-09-01 | 12
Times Square | Retail | 1741 | Concept & Design Rendering | 2026-02-12 | 2026-05-01 | 78
Times Square | Retail | 1741 | Detailed Drawings Package | 2026-05-01 | 2026-05-15 | 14
Times Square | Retail | 1741 | Landlord Sign Off and Approvals | 2026-05-15 | 2026-06-15 | 31
Times Square | Retail | 1741 | Hoarding | 2026-06-15 | 2026-07-15 | 30
Times Square | Retail | 1741 | Launch | 2026-07-15 | 2026-08-05 | 21
Times Square | Retail | 1741 | Merchandising | 2026-08-05 | 2026-09-30 | 56
Times Square | F&B | 1000 | Concept & Design Rendering | 2026-02-12 | 2026-05-01 | 78
Times Square | F&B | 1000 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0
Times Square | F&B | 1000 | Licensing Submission | 2026-03-01 | 2026-05-15 | 75
Times Square | F&B | 1000 | Detailed Drawings Package | 2026-05-15 | 2026-05-15 | 0
Times Square | F&B | 1000 | Landlord Sign Off and Approvals | 2026-05-15 | 2026-06-15 | 31
Times Square | F&B | 1000 | Hoarding | 2026-06-15 | 2026-07-15 | 30
Times Square | F&B | 1000 | Provisional License in Place | 2026-07-15 | 2026-08-05 | 21
Times Square | F&B | 1000 | Launch | 2026-08-05 | 2026-09-20 | 46
Times Square | F&B | 1000 | Final Launch | 2026-09-20 | 2026-09-30 | 10
Canton Road | Retail | 1228 | Concept & Design Rendering | 2026-02-12 | 2026-05-15 | 92
Canton Road | Retail | 1228 | Detailed Drawings Package | 2026-05-15 | 2026-06-01 | 17
Canton Road | Retail | 1228 | Landlord Sign Off and Approvals | 2026-06-01 | 2026-07-01 | 30
Canton Road | Retail | 1228 | Hoarding | 2026-07-01 | 2026-07-31 | 30
Canton Road | Retail | 1228 | Launch | 2026-07-31 | 2026-08-10 | 10
Canton Road | Retail | 1228 | Merchandising | 2026-08-10 | 2026-09-30 | 51
Canton Road | F&B | 963 | Concept & Design Rendering | 2026-02-12 | 2026-05-15 | 92
Canton Road | F&B | 963 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0
Canton Road | F&B | 963 | Licensing Submission | 2026-03-01 | 2026-06-01 | 92
Canton Road | F&B | 963 | Detailed Drawings Package | 2026-06-01 | 2026-06-01 | 0
Canton Road | F&B | 963 | Landlord Sign Off and Approvals | 2026-06-01 | 2026-07-01 | 30
Canton Road | F&B | 963 | Hoarding | 2026-07-01 | 2026-07-31 | 30
Canton Road | F&B | 963 | Provisional License in Place | 2026-07-31 | 2026-08-10 | 10
Canton Road | F&B | 963 | Launch | 2026-08-10 | 2026-09-20 | 41
Canton Road | F&B | 963 | Final Launch | 2026-09-20 | 2026-09-30 | 10
INTENSITY >
bottum-up calculation (Concept Design / 3D's / DD only)
4 projects running concurrently
88 weeks of design & drawing work
in 22 weeks
resources > assuming minimum 4 people
day rates > 12000 + 8000 + 5000 + 5000 = 30000 p/d
x 5 days = 150k p/w
[8 empty] | x 22 weeks = HKD 3.3M | [13 empty] | what is LC's budget?
fee as
[8 empty] | top down fee calc based on square footage | [10 empty] | construction cost based on square footage | [10 empty] | CC %
[6 empty] | LOW Q | Feb F 13: 10,500 sq ft x 300 hkd p/sq ft; Feb T 19: >; Feb F 20: 3.15M; Feb T 24: 10,500 sq ft x 2500 hkd p/sq ft; March M 2: >; March T 3: 26.25M; March S 7: 8.3
[8 empty] | 10,500 sq ft x 400 hkd p/sq ft | [5 empty] | > | 4.2M |  |  |  | 10,500 sq ft x 3000 hkd p/sq ft | [5 empty] | > | 31.5M
[8 empty] | 10,500 sq ft x 500 hkd p/sq ft | [5 empty] | > | 5.25M |  |  |  | 10,500 sq ft x 3500 hkd p/sq ft | [5 empty] | > | 36.75M
[8 empty] | 10,500 sq ft x 600 hkd p/sq ft | [5 empty] | > | 6.3M |  |  |  | 10,500 sq ft x 4000 hkd p/sq ft | [5 empty] | > | 42M
[8 empty] | 10,500 sq ft x 700 hkd p/sq ft | [5 empty] | > | 7.35M |  |  |  | 10,500 sq ft x 4500 hkd p/sq ft | [5 empty] | > | 47.25M
[6 empty] | HIGH Q | Feb F 13: 10,500 sq ft x 800 hkd p/sq ft; Feb T 19: >; Feb F 20: 8.4M; Feb T 24: 10,500 sq ft x 5000 hkd p/sq ft; March M 2: >; March T 3: 52.5M; March S 7: 6.25

## LC
Store | Section | Space (sq ft) | Task | Start Date | End Date | Duration (Days) | W1 Feb 12-18 | W2 Feb 19-25 | W3 Feb 26-Mar 4 | W4 Mar 5-11 | W5 Mar 12-18 | W6 Mar 19-25 | W7 Mar 26-Apr 1 | W8 Apr 2-8 | W9 Apr 9-15 | W10 Apr 16-22 | W11 Apr 23-29 | W12 Apr 30-May 6 | W13 May 7-13 | W14 May 14-20 | W15 May 21-27 | W16 May 28-Jun 3 | W17 Jun 4-10 | W18 Jun 11-17 | W19 Jun 18-24 | W20 Jun 25-Jul 1 | W21 Jul 2-8 | W22 Jul 9-15 | W23 Jul 16-22 | W24 Jul 23-29 | W25 Jul 30-Aug 5 | W26 Aug 6-12 | W27 Aug 13-19 | W28 Aug 20-26 | W29 Aug 27-Sep 2 | W30 Sep 3-9 | W31 Sep 10-16 | W32 Sep 17-23 | W33 Sep 24-30
IFC | Retail | 3004 | Concept & Design Rendering | 2026-02-12 | 2026-03-31 | 47 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 35d
IFC | Retail | 3004 | Detailed Drawings Package | 2026-03-31 | 2026-04-20 | 47: 20; 35d: 8 | 9 | 10 | 15d
IFC | Retail | 3004 | Landlord Sign Off and Approvals | 2026-04-20 | 2026-05-15 | 47: 25 |  |  | X | X | X | X
IFC | Retail | 3004 | Hoarding | 2026-05-15 | 2026-05-31 | 47: 16 | [5 empty] | X | X | X
IFC | Retail | 3004 | Launch | 2026-05-31 | 2026-06-10 | 47: 10 | [8 empty] | X
IFC | Retail | 3004 | Merchandising | 2026-06-10 | 2026-07-15 | 47: 35 | [8 empty] | X | X | X | X | X | X
IFC | F&B | 1200 | Concept & Design Rendering | 2026-02-12 | 2026-03-31 | 47 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
IFC | F&B | 1200 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 35 47: 0; 35 3: X
IFC | F&B | 1200 | Licensing Submission | 2026-03-01 | 2026-04-20 | 50 |  |  | X | X | X | X | X | X | X | X
IFC | F&B | 1200 | Detailed Drawings Package | 2026-04-20 | 2026-04-20 | 35 47: 0 |  |  | 9 | 10 | 11 | 12
IFC | F&B | 1200 | Landlord Sign Off and Approvals | 2026-04-20 | 2026-05-15 | 35 47: 25
IFC | F&B | 1200 | Hoarding | 2026-05-15 | 2026-05-31 | 35 47: 16 | [5 empty] | X | X | X
IFC | F&B | 1200 | Provisional License in Place | 2026-05-31 | 2026-07-20 | 35 47: 50 | [8 empty] | X | X | X | X | X | X | X
IFC | F&B | 1200 | Launch | 2026-07-20 | 2026-09-15 | 35 47: 57 | [14 empty] | X | X | X | X | X | X | X | X | X | X
Pacific Place | Retail | 863 | Concept & Design Rendering | 2026-02-12 | 2026-04-15 | 62 | X | X | 1 | 2 | 3 | 4 | 5 | 6 | 7
Pacific Place | Retail | 863 | Detailed Drawings Package | 2026-04-15 | 2026-05-01 | 16 | [9 empty] | 8 | 9 | 10
Pacific Place | Retail | 863 | Landlord Sign Off and Approvals | 2026-05-01 | 2026-06-01 | 31 | [11 empty] | X | X | X | X | X
Pacific Place | Retail | 863 | Hoarding | 2026-06-01 | 2026-06-20 | 19 | [16 empty] | X | X | X
Pacific Place | Retail | 863 | Launch | 2026-06-20 | 2026-07-05 | 15 | [18 empty] | X | X
Pacific Place | Retail | 863 | Merchandising | 2026-07-05 | 2026-09-01 | 58 | [19 empty] | X | X | X | X | X | X | X | X | X
Pacific Place | F&B | 500 | Concept & Design Rendering | 2026-02-12 | 2026-04-15 | 62 | X | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Pacific Place | F&B | 500 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0 | bar: 2
Pacific Place | F&B | 500 | Licensing Submission | 2026-03-01 | 2026-05-01 | 61 | [9 empty] | X | X | X | bar: 2 to 8
Pacific Place | F&B | 500 | Detailed Drawings Package | 2026-05-01 | 2026-05-01 | 0 | [11 empty] | 9 | 10 | 11 | 12
Pacific Place | F&B | 500 | Landlord Sign Off and Approvals | 2026-05-01 | 2026-06-01 | 31 | [15 empty] | X
Pacific Place | F&B | 500 | Hoarding | 2026-06-01 | 2026-06-20 | 19 | [16 empty] | X | X | X
Pacific Place | F&B | 500 | Provisional License in Place | 2026-06-20 | 2026-07-05 | 15 | [18 empty] | X | X
Pacific Place | F&B | 500 | Launch | 2026-07-05 | 2026-08-20 | 46 | [19 empty] | X | X | X | X | X | X | X | X
Pacific Place | F&B | 500 | Final Launch | 2026-08-20 | 2026-09-01 | 12 | [26 empty] | X | X
Times Square | Retail | 1741 | Concept & Design Rendering | 2026-02-12 | 2026-05-01 | 78 | X | X | X | X | 1 | 2 | 3 | 4 | 5 | 6 | 7 | X
Times Square | Retail | 1741 | Detailed Drawings Package | 2026-05-01 | 2026-05-15 | 14 | [11 empty] | 8 | 9 | 10
Times Square | Retail | 1741 | Landlord Sign Off and Approvals | 2026-05-15 | 2026-06-15 | 31 | [13 empty] | X | X | X | X | X
Times Square | Retail | 1741 | Hoarding | 2026-06-15 | 2026-07-15 | 30 | [16 empty] | X | X | X | X | X
Times Square | Retail | 1741 | Launch | 2026-07-15 | 2026-08-05 | 21 | [20 empty] | X | X | X
Times Square | Retail | 1741 | Merchandising | 2026-08-05 | 2026-09-30 | 56 | [24 empty] | X | X | X | X | X | X | X | X | X
Times Square | F&B | 1000 | Concept & Design Rendering | 2026-02-12 | 2026-05-01 | 78 | X | X | X | X | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Times Square | F&B | 1000 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0 |  |  | X
Times Square | F&B | 1000 | Licensing Submission | 2026-03-01 | 2026-05-15 | 75 |  |  | X | X | [8 empty] | X | X | bar: 1 to 8
Times Square | F&B | 1000 | Detailed Drawings Package | 2026-05-15 | 2026-05-15 | 0 | [13 empty] | X
Times Square | F&B | 1000 | Landlord Sign Off and Approvals | 2026-05-15 | 2026-06-15 | 31 | [13 empty] | X | 9 | 10 | 11 | 12
Times Square | F&B | 1000 | Hoarding | 2026-06-15 | 2026-07-15 | 30 | [16 empty] | X | X | X | X | X
Times Square | F&B | 1000 | Provisional License in Place | 2026-07-15 | 2026-08-05 | 21 | [20 empty] | X | X | X
Times Square | F&B | 1000 | Launch | 2026-08-05 | 2026-09-20 | 46 | [24 empty] | X | X | X | X | X | X | X | X
Times Square | F&B | 1000 | Final Launch | 2026-09-20 | 2026-09-30 | 10 | [31 empty] | X | X
Canton Road | Retail | 1228 | Concept & Design Rendering | 2026-02-12 | 2026-05-15 | 92 | X | X | X | X | X | X | 1 | 2 | 3 | 4 | 5 | 6 | 7 | X
Canton Road | Retail | 1228 | Detailed Drawings Package | 2026-05-15 | 2026-06-01 | 17 | [13 empty] | 8 | 9 | 10
Canton Road | Retail | 1228 | Landlord Sign Off and Approvals | 2026-06-01 | 2026-07-01 | 30 | [16 empty] | X | X | X | X
Canton Road | Retail | 1228 | Hoarding | 2026-07-01 | 2026-07-31 | 30 | [19 empty] | X | X | X | X | X
Canton Road | Retail | 1228 | Launch | 2026-07-31 | 2026-08-10 | 10 | [24 empty] | X | X
Canton Road | Retail | 1228 | Merchandising | 2026-08-10 | 2026-09-30 | 51 | [25 empty] | X | X | X | X | X | X | X | X
Canton Road | F&B | 963 | Concept & Design Rendering | 2026-02-12 | 2026-05-15 | 92 | X | X | X | X | X | X | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Canton Road | F&B | 963 | Licensing Contractor on Board | 2026-03-01 | 2026-03-01 | 0 |  |  | X
Canton Road | F&B | 963 | Licensing Submission | 2026-03-01 | 2026-06-01 | 92 |  |  | X | X | X | X | [8 empty] | X | X | X | bar: 1 to 8
Canton Road | F&B | 963 | Detailed Drawings Package | 2026-06-01 | 2026-06-01 | 0 | [16 empty] | X
Canton Road | F&B | 963 | Landlord Sign Off and Approvals | 2026-06-01 | 2026-07-01 | 30 | [16 empty] | 9 | 10 | 11 | 12
Canton Road | F&B | 963 | Hoarding | 2026-07-01 | 2026-07-31 | 30 | [19 empty] | X | X | X | X | X
Canton Road | F&B | 963 | Provisional License in Place | 2026-07-31 | 2026-08-10 | 10 | [24 empty] | X | X
Canton Road | F&B | 963 | Launch | 2026-08-10 | 2026-09-20 | 41 | [25 empty] | X | X | X | X | X | X | X
Canton Road | F&B | 963 | Final Launch | 2026-09-20 | 2026-09-30 | 10 | [31 empty] | X | X
[5 empty] | INTENSITY > |  | 2 | 3 | 4 | 4 | 6 | 6 | 8 | 8 | 7 | 6 | 6 | 7 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | 1 | 88
bottum-up calculation (Concept Design / 3D's / DD only)
4 projects running concurrently
88 weeks of design & drawing work
in 22 weeks
resources > assuming minimum 4 people
day rates > 12000 + 8000 + 5000 + 5000 = 30000 p/d
x 5 days = 150k p/w
[8 empty] | x 22 weeks = HKD 3.3M | [13 empty] | what is LC's budget?
fee as
[8 empty] | top down fee calc based on square footage |  |  |  |  | 7: construction cost based on square footage | [9 empty] | CC %
[6 empty] | LOW Q |  | 10,500 sq ft x 300 hkd p/sq ft |  |  |  |  | 2: >; 3: 3.15M; 7: 10,500 sq ft x 2500 hkd p/sq ft |  |  |  |  | > | 26.25M |  |  |  | 8.3
[8 empty] | 10,500 sq ft x 400 hkd p/sq ft |  |  |  |  | 2: >; 3: 4.2M; 7: 10,500 sq ft x 3000 hkd p/sq ft |  |  |  |  | > | 31.5M
[8 empty] | 10,500 sq ft x 500 hkd p/sq ft |  |  |  |  | 2: >; 3: 5.25M; 7: 10,500 sq ft x 3500 hkd p/sq ft |  |  |  |  | > | 36.75M
[8 empty] | 10,500 sq ft x 600 hkd p/sq ft |  |  |  |  | 2: >; 3: 6.3M; 7: 10,500 sq ft x 4000 hkd p/sq ft |  |  |  |  | > | 42M
[8 empty] | 10,500 sq ft x 700 hkd p/sq ft |  |  |  |  | 2: >; 3: 7.35M; 7: 10,500 sq ft x 4500 hkd p/sq ft |  |  |  |  | > | 47.25M
[6 empty] | HIGH Q |  | 10,500 sq ft x 800 hkd p/sq ft |  |  |  |  | 2: >; 3: 8.4M; 7: 10,500 sq ft x 5000 hkd p/sq ft |  |  |  |  | > | 52.5M |  |  |  | 6.25